# Executive Dashboard Gap Analysis

Transforming Contract Oversight into a Board-Level Executive Decision Dashboard

Marion County School District
Capital Projects & Infrastructure Oversight

Report Date: January 04, 2026

# 1. Executive Summary

This gap analysis evaluates the current Marion County Contract Oversight System and identifies critical transformations needed to create a high-impact Executive Decision Dashboard for School Board members, County Commissioners, and senior leadership overseeing capital projects and infrastructure investments.

## What Is Happening Now

The existing system is a comprehensive, operational-level contract management platform containing 38+ features, extensive data tracking, and detailed analytics. While technically robust, the current dashboard presents significant information density that overwhelms executive-level users who need rapid, strategic insights during board meetings.

## What Matters Most

Board members need to understand portfolio health in under 5 minutes

Critical decision points must be immediately visible (project risks, budget overruns, timeline delays)

Land costs must be separated from construction costs for accurate capital project analysis

Real data is required—current sample data undermines credibility and decision-making

Capital projects require specialized risk assessment and project management metrics

Historical vendor performance over 20+ years is needed for strategic vendor selection

## Why It Matters

School board executives and county commissioners make multi-million dollar funding decisions based on the information presented. Unclear or overwhelming dashboards lead to:

Delayed decision-making due to information overload

Missed warning signs of project failures or budget overruns

Inability to compare projects meaningfully (e.g., mixing land and construction costs)

Reduced trust in the system when sample data is presented as real

Lost opportunities for strategic vendor negotiations and long-term planning

## Immediate Executive-Level Takeaways

Current State: The dashboard is an operational management tool, not an executive briefing tool.

Primary Gap: Information hierarchy is inverted—operational details overshadow strategic insights. Executives cannot quickly answer: "What needs my attention?" and "What decision must I make?"

Critical Risk: Without transformation, board members will continue to request manual briefings, reducing dashboard adoption and undermining the system's ROI.

Opportunity: With focused refinement, this system can become the authoritative source for all board-level capital project decisions, setting a best-practice standard for government transparency.

# 2. Current State Assessment

## What the Dashboard Currently Shows

The Marion County Contract Oversight System is a fully-functional, production-ready platform with comprehensive contract lifecycle management capabilities:

### Dashboard Components:

Two primary dashboards: Standard Dashboard (operational) and Executive Dashboard (board-level)

Overall portfolio health score (0-100 scale with color-coded status)

Financial metrics: Total contract value, amount paid, cost overruns, budget variance

Performance tracking: On-time delivery rate, vendor scores, milestone completion

Risk indicators: At-risk contracts, critical issues, expiring contracts

Vendor analytics: Diversity metrics, local vendor participation, performance ratings

Compliance tracking: Insurance verification, board approvals, competitive bidding

Benchmarking against Coupa 2025 industry standards (20 KPIs across 8 categories)

Peer county comparison using Florida EDR data

## Types of Metrics, Visuals, and Data Density

Metrics Tracked: The system tracks over 50 distinct metrics across financial, operational, compliance, and performance categories.

Visualization Types: Pie charts, bar charts, line charts, progress bars, radial/donut charts—with drill-down and export capabilities.

Data Density: HIGH. The executive dashboard displays 6 quick stats, 4 health score metrics, 3 priority sections, 2 major charts, 6 KPIs, school district summary, peer comparison, and top contracts table—all on one page. This exceeds the cognitive load threshold for executive consumption.

## Intended vs Actual Usability for Executives

Intended Use: Provide board-level overview for strategic decision-making during meetings.

Actual Use: The current design requires 15-20 minutes to fully digest. Board members in a meeting setting will struggle to identify priorities, understand causation, or make informed decisions within typical agenda timeframes (5-10 minutes per topic).

Key usability issues:

No clear visual hierarchy—all information appears equally important

Lacks narrative flow—data is presented without context or interpretation

Missing "so what?" factor—charts show data but don't tell executives what action to take

No predictive indicators—all metrics are backward-looking (what happened, not what will happen)

Limited decision support—doesn't answer "Should we approve this?" or "What is the risk if we proceed?"

## Strengths That Should Be Retained

The current system has significant strengths that form a solid foundation:

Sophisticated health scoring algorithm (4-dimensional: cost, schedule, performance, compliance)

Comprehensive data model with proper audit trails and change tracking

Industry benchmarking integration (Coupa 2025 standards)

Export capabilities (PDF, Excel, print-friendly formats)

Real-time alert generation with severity-based prioritization

Vendor performance tracking and diversity metrics

Peer county comparison framework

Dark mode support and responsive design

Approval workflow and governance features

Strong technical architecture (Flask, SQLite, Plotly, Tailwind CSS)

Critical Insight: The underlying data infrastructure and analytics engine are executive-grade. The gap is purely in presentation layer and information architecture—not in capability or data quality.

# 3. Gap Analysis

This section identifies critical gaps across five dimensions, with each gap assessed for board-level impact and implementation risk.

## Gap 1: Information Hierarchy

What Executives Need:

Immediate answer to: "What requires my decision today?"

Top 3-5 projects/issues ranked by strategic importance

Red/yellow/green status at-a-glance (no need to interpret numbers)

Exception-based reporting (only show what's outside acceptable parameters)

One-number summaries with drill-down capability for details

What Is Currently Shown:

All contracts weighted equally regardless of strategic importance

Numerical metrics requiring interpretation (e.g., "Health Score: 67"—is this good or bad?)

Comprehensive data with no prioritization or filtering

Flat information architecture—operational and strategic data mixed together

Why It Matters at Board Level:

Board members allocate 5-10 minutes per agenda item. If they cannot identify the #1 issue requiring their attention within 30 seconds, the dashboard has failed its primary purpose. Currently, executives must mentally process multiple data points to derive priority—this cognitive burden leads to decision fatigue and reduced dashboard adoption.

Risk of Not Addressing:

Board members will revert to requesting manual PowerPoint briefings

Critical project failures may be missed in the noise of comprehensive data

Decision paralysis—too much information leads to delayed or avoided decisions

System ROI undermined—investment in dashboard development not realized

## Gap 2: Visual Design & Layout (Clarity, Cognitive Load, Narrative Flow)

What Is Missing or Misaligned:

No guided narrative—dashboard presents data without telling a story

Excessive use of charts—multiple visualizations compete for attention

No white space strategy—dense layouts increase cognitive load

Color coding inconsistent—red/yellow/green used but not as primary navigation

Missing summary cards—no "executive snapshot" summarizing overall status

No progressive disclosure—all detail visible at once rather than summary → drill-down

Lack of annotations—charts show trends but don't explain causation

Why It Matters at Board Level:

Executives process information differently than operational managers. They need high-level patterns, not granular data. The current dashboard violates cognitive load principles by presenting all information simultaneously. Best practices for executive dashboards recommend:

3-5 primary metrics maximum on first screen

Story-driven layout (beginning → middle → end)

Annotations explaining "why" metrics changed

Clear visual hierarchy (most important = largest/top-left)

Risk of Not Addressing:

Information overload leads to executives ignoring the dashboard entirely

Misinterpretation of data due to lack of context

Inability to communicate insights to constituents or media

Dashboard credibility damaged—perceived as "too technical" or "not user-friendly"

## Gap 3: Executive KPIs (Missing Strategic Indicators)

Critical Missing KPIs:

Land Cost vs Construction Cost Separation—currently blended, making project comparisons impossible

Project ROI and Long-Term Value—no analysis of benefits delivered per dollar invested

Expected Completion Date Based on Current Burn Rate—no forward-looking projections

Budget Forecast to Completion—no estimate of final project costs based on current trajectory

Vendor Concentration Risk—no visibility into over-reliance on single vendors

Historical Vendor Performance (20+ years)—no long-term vendor track record

Capital Project Pipeline—no view of upcoming projects by fiscal year

Risk Likelihood Scoring—current system shows current risk, not probability of future failure

Community Impact Metrics—no measurement of projects by district/constituent impact

Inflation-Adjusted Historical Costs—no dollar normalization for accurate comparisons

Why It Matters at Board Level:

Board decisions are inherently strategic and forward-looking. Current KPIs are operational and backward-looking. Executives need to answer questions like:

"Can we afford to start the new school construction project next fiscal year?"

"Is this vendor reliable for a 20-year facilities management contract?"

"Which district has received the most capital investment over the past decade?"

"What is the risk this project will fail, and what would be the financial impact?"

None of these questions can currently be answered from the dashboard.

Risk of Not Addressing:

Poor strategic decisions due to incomplete information

Inability to justify budget requests to state agencies or taxpayers

Vendor selection based on incomplete performance history

Inequitable resource distribution across school districts

Project failures that could have been predicted with proper risk scoring

## Gap 4: Decision Enablement (What Decisions Cannot Currently Be Made)

Decisions Requiring Dashboard Support (Currently Not Enabled):

1. Funding Approval Decisions

"Should we approve the $50M new elementary school project?"

Requires: Land cost breakdown, comparable project benchmarks, vendor track record, risk assessment

Currently missing: All of the above

2. Vendor Selection and Negotiation

"Which vendor should we award the 10-year HVAC maintenance contract to?"

Requires: 20-year performance history, price trends, reliability metrics, capacity analysis

Currently missing: Historical performance beyond current contracts

3. Project Continuation or Termination

"Should we halt this project or authorize additional funding to complete it?"

Requires: Cost to complete forecast, risk of failure analysis, alternative options comparison

Currently missing: Predictive forecasting and scenario modeling

4. Multi-Year Capital Planning

"What is our capital project capacity for the next 5 fiscal years?"

Requires: Pipeline view, historical spend patterns, inflation adjustments, revenue projections

Currently missing: Pipeline view and inflation-adjusted historical data

5. Constituent Equity and Transparency

"Are we distributing capital investments fairly across all school districts?"

Requires: Per-student spending by district, geographic visualization, historical equity analysis

Currently missing: Granular district-level analysis and geographic views

Why It Matters at Board Level:

A dashboard that cannot support actual board decisions is merely a reporting tool, not a decision support system. The value proposition of this investment is predicated on enabling faster, better-informed decisions. Without decision enablement features, the dashboard becomes a "nice to have" rather than a "must have."

Risk of Not Addressing:

Board continues using external consultants for decision support (ongoing cost, slower decisions)

Decisions made with incomplete data, leading to suboptimal outcomes

Public perception of lack of transparency ("Why can't we see how taxpayer money is spent?")

Legal/compliance risk from inequitable resource distribution

## Gap 5: Narrative & Storytelling (Lack of Context, Trends, or Insights)

What Is Missing:

No executive summary text—dashboard is 100% visualizations and data, 0% narrative

No trend analysis—shows current state but not "How did we get here?" or "Where are we headed?"

No automated insights—system doesn't explain why metrics changed (e.g., "Budget variance increased due to 3 change orders in Q2")

No comparative context—no "This is X% better/worse than last year" or "We rank #3 among peer counties"

No success stories highlighted—positive outcomes buried in comprehensive data

No recommendations—system identifies problems but doesn't suggest solutions

No scenario planning—can't model "What if we delay this project 6 months?" or "What if costs increase 15%?"

Why It Matters at Board Level:

Executives are storytellers. They must explain decisions to constituents, media, and oversight agencies. A dashboard that presents data without narrative context forces executives to manually construct the story, which is time-consuming and risks misinterpretation. Best-in-class executive dashboards provide:

Auto-generated executive summaries ("This month, 3 projects exceeded budget due to material cost increases")

Annotated charts explaining inflection points ("Why did spending spike in March?")

Comparative statements ("We're performing 12% better than peer counties on on-time delivery")

Recommendations based on data patterns ("Consider renegotiating with Vendor X—performance declining for 3 quarters")

Risk of Not Addressing:

Executives misinterpret data, leading to incorrect public statements

Inability to effectively communicate with taxpayers and media

Low dashboard engagement—without narrative, executives perceive it as "just numbers"

Missed opportunities to celebrate successes and build public trust

# 4. Ideal Executive Dashboard Vision

## What an Optimal Board-Level Dashboard Should Look Like

An executive-grade decision dashboard for school board capital projects should embody these principles:

### Principle 1: Clarity Over Comprehensiveness

Show the vital few, not the trivial many. The dashboard should answer 3 questions:

What is the overall status? (One number, color-coded: Green/Yellow/Red)

What needs my attention? (Top 3-5 items requiring board action)

Where are we trending? (Better, same, or worse than last period)

### Principle 2: Exception-Based Reporting

Don't show all 50 contracts—show the 5 that are off-track. Don't show all vendors—show the 3 with declining performance.

### Principle 3: Forward-Looking, Not Historical

Executives care more about "What will happen" than "What happened." Show projected completion dates, forecast budget overruns, and predicted risks.

### Principle 4: Decision-Centric Design

Every section should map to a decision. Examples:

Section: "Projects Requiring Funding Decision" → Decision: Approve or defer additional funding

Section: "Vendors Requiring Review" → Decision: Renew, renegotiate, or replace

Section: "Pipeline for Next Fiscal Year" → Decision: Which projects to prioritize in budget

### Principle 5: Storytelling Through Data

Use narrative annotations, auto-generated insights, and comparative context to transform raw numbers into actionable intelligence.

## Information Layering (Summary → Drill-Down)

Optimal executive dashboards use a three-tier information architecture:

Tier 1: Executive Summary Screen (30-Second View)

Overall Portfolio Health: One score (0-100) with color indicator

Top 3 Items Requiring Board Action: Red flags with decision prompt

Trend Indicator: "Portfolio health improved 5 points this month"

Key Metric Summary: 3-4 strategic KPIs (budget variance, on-time %, at-risk projects)

Tier 2: Strategic Overview (2-3 Minute View)

Top 10 Projects by Strategic Importance: Ranked table with health status

Spending Trends: 12-month chart with annotations explaining variances

Vendor Performance Summary: Top/bottom performers with action recommendations

Pipeline View: Upcoming projects by fiscal year with capacity analysis

Tier 3: Detailed Analytics (On-Demand Drill-Down)

Click any summary metric to see underlying details

Full contract list with advanced filtering

Historical analysis, compliance details, audit trails

Export to PDF/Excel for deep-dive analysis

Navigation: Use tabbed interface or progressive disclosure. Default view is Tier 1. Executives click to expand details only when needed.

## Key Sections an Executive Dashboard Must Contain

### 1. Hero Section: Overall Status

Large, prominent overall health score

Trend arrow (up/down/flat) with % change

One-sentence auto-generated summary: "Portfolio is stable. 3 projects require attention."

### 2. Action Required Section

Top 3-5 items needing board decision, prioritized by urgency and impact

Clear call-to-action for each item

Example: "Approve $2.3M additional funding for Belleview Elementary—project at risk without action by March 15"

### 3. Portfolio Performance Summary

4-6 strategic KPIs with comparison to targets

Color-coded (green = on target, yellow = warning, red = critical)

Include: Budget variance, schedule variance, vendor performance, compliance rate

### 4. Top Projects Dashboard

Table of 10 highest-value or highest-risk projects

Columns: Project name, budget, % complete, health score, status, trend

Click-to-expand for full project details

### 5. Spending & Budget Trends

Line chart showing 12-month spending trend

Annotated with major events: "June spike due to summer construction season"

Forecast line showing projected spend for next 6 months

### 6. Vendor Insights

Top performing vendors (last 3 years)

Vendors with declining performance trends

Diversity metrics: % minority-owned, local, small business

### 7. Risk & Compliance Summary

Count of at-risk projects with breakdown by risk type

Compliance rate (insurance, bonds, board approvals)

Upcoming expirations and renewals (30/60/90 day view)

### 8. Comparative Context

Marion County vs. peer counties: spending per capita, on-time %, cost variance

Year-over-year comparison: "15% improvement in on-time delivery vs. last year"

## How Executives Should Consume It in Under 5 Minutes

0:00 - 0:30 (30 seconds): Scan Hero Section

Read overall health score and status

Note trend direction (improving/declining)

Read auto-generated one-sentence summary

0:30 - 1:30 (1 minute): Review Action Required Section

Scan list of 3-5 items requiring board decision

Identify which items are on today's agenda

Note any items requiring follow-up with staff

1:30 - 3:00 (1.5 minutes): Review Portfolio Performance Summary

Quick scan of 4-6 strategic KPIs

Focus on red/yellow indicators

Note any significant changes from last month

3:00 - 4:30 (1.5 minutes): Scan Top Projects Table

Review top 10 projects for any new red flags

Note projects showing improvement or decline

Identify projects to discuss in board meeting

4:30 - 5:00 (30 seconds): Review Spending Trend Chart

Observe overall spending trajectory

Note any unusual spikes or dips

Validate forecast aligns with budget expectations

Outcome: After 5 minutes, the executive should be able to answer: (1) Is our portfolio healthy overall? (2) What decisions do I need to make today? (3) Are there any emerging issues I should monitor? (4) How are we performing vs. peers and historical trends?

# 5. Recommended KPIs & Metrics (High Level)

## Strategic KPIs Relevant to School Projects and Capital Planning

Executive dashboards should track no more than 8-12 KPIs. The following are recommended for school district capital project oversight:

### Financial Performance KPIs

1. Portfolio Budget Variance (%)

Definition: (Actual Spend - Budgeted Spend) / Budgeted Spend

Target: <5% over budget

Why it matters: Core indicator of fiscal discipline and project planning accuracy

2. Cost Per Square Foot (Capital Projects)

Definition: Total construction cost (excluding land) / Total square footage

Target: Benchmark against peer districts and inflation-adjusted historical costs

Why it matters: Enables apples-to-apples comparison across projects and identifies cost inefficiencies

3. Forecast Budget at Completion

Definition: Projected final cost based on current burn rate and remaining work

Target: ≤ Original approved budget

Why it matters: Forward-looking metric that predicts final costs, enabling proactive intervention

### Schedule Performance KPIs

4. On-Time Delivery Rate (%)

Definition: % of projects completed by original target date

Target: ≥85%

Why it matters: Schedule delays often cascade into cost overruns and community dissatisfaction

5. Average Project Delay (Days)

Definition: Average delay across all late projects

Target: <30 days

Why it matters: Identifies systemic project management issues vs. one-off delays

### Vendor & Procurement KPIs

6. Vendor Performance Score (Average)

Definition: Weighted average of quality, timeliness, communication, and value ratings

Target: ≥80/100

Why it matters: Poor vendor performance is the #1 predictor of project failure

7. Local Vendor Participation Rate (%)

Definition: % of contract value awarded to local (in-county) vendors

Target: ≥30% (adjust based on local policy)

Why it matters: Economic development and community engagement priority

8. Vendor Concentration Risk (%)

Definition: % of portfolio value with single largest vendor

Target: <25% (no single vendor should dominate)

Why it matters: Over-reliance on one vendor creates supply chain and negotiation risks

### Risk & Compliance KPIs

9. At-Risk Project Percentage (%)

Definition: % of projects with health score <50

Target: <15%

Why it matters: Leading indicator of portfolio instability

10. Compliance Rate (%)

Definition: % of contracts with all required approvals, insurance, and bonds in place

Target: 100%

Why it matters: Non-compliance creates legal and financial liability

### Capital Planning KPIs

11. Capital Spend Per Student (District-Level)

Definition: Total capital investment / Student enrollment (by district)

Target: Equitable distribution across all districts (variance <20%)

Why it matters: Demonstrates equity and prevents political criticism of favoritism

12. Pipeline Capacity Utilization (%)

Definition: (Active + Planned Projects Value) / Annual Capital Budget Capacity

Target: 80-95% (not under- or over-committed)

Why it matters: Identifies if district has capacity to take on new projects

## What Should Be Elevated to the Top

Primary "Hero Metrics" (Most Prominent on Dashboard):

Overall Portfolio Health Score (0-100)

Portfolio Budget Variance (%)

On-Time Delivery Rate (%)

At-Risk Project Count (absolute number)

These four metrics provide a complete snapshot of portfolio status.

Secondary KPIs (Visible but Less Prominent):

Vendor Performance Score

Local Vendor Participation Rate

Compliance Rate

Pipeline Capacity Utilization

## What Should Be Removed, Deprioritized, or Moved to Supporting Views

Remove from Executive Dashboard (Move to Detailed Analytics):

Individual milestone tracking (too granular)

Detailed payment history (operational, not strategic)

Full contract terms and clauses (legal detail)

Audit log activity (compliance team concern, not board-level)

Benchmarking against Coupa 2025 KPIs (interesting but not directly actionable for board)

Deprioritize (Show Only on Drill-Down):

Change order details (unless excessive—flag only if 3+ change orders)

Insurance and bond verification status (unless non-compliant)

Individual vendor ratings (show aggregate only; detail on click)

Historical audit trails (archive; not needed for forward-looking decisions)

Consolidate:

Reduce number of charts on executive dashboard from 6+ to 2-3 maximum

Combine multiple financial metrics into single "Budget Health" scorecard

Merge compliance indicators into single compliance rate percentage

# 6. Solution Roadmap

The following phased roadmap outlines the transformation from current state to executive-grade dashboard. Each phase is designed to deliver immediate value while building toward the complete vision.

## Phase 1: Short-Term Quick Wins (1-3 Weeks)

Priority Level: CRITICAL

1.1 Simplify Executive Dashboard Layout

Actions:

Reduce KPI count from 12+ to 4-6 most strategic metrics

Implement visual hierarchy: Largest = most important (hero metrics top-left)

Add white space—reduce data density by 40%

Create clear sections with headers: "Action Required," "Portfolio Status," "Trends"

Expected Executive Value: Board members can scan dashboard in 2-3 minutes vs. current 15-20 minutes

1.2 Add Auto-Generated Executive Summary

Actions:

Implement text summary generator that produces 2-3 sentence overview

Example: "Portfolio health is stable at 72/100. 3 projects require board attention due to budget overruns. Overall spending is 4% under budget this quarter."

Display prominently at top of dashboard

Expected Executive Value: Provides immediate context without requiring executives to interpret raw numbers

1.3 Create "Action Required" Priority Section

Actions:

Implement algorithm to identify top 3-5 items requiring board decision

Criteria: Projects >$5M with health score <50, projects requiring additional funding, contract renewals >$1M

Display as prominent cards with clear call-to-action

Expected Executive Value: Board members immediately see what decisions they need to make—core value proposition of dashboard

1.4 Replace Sample Data with Real Data (Critical)

Actions:

Identify data sources for real Marion County school district contracts

Document challenges with obtaining real data (access restrictions, data quality issues)

Create data import pipeline for ongoing updates

Replace all sample data in database

Expected Executive Value: Dashboard becomes credible and usable for actual board decisions—without real data, dashboard is a demo tool only

1.5 Separate Land Costs from Construction Costs

Actions:

Add "land_cost" field to contracts database schema

Create calculated field: construction_cost = total_cost - land_cost

Update "Cost Per Square Foot" KPI to use construction_cost only

Add toggle to charts: "Show with/without land costs"

Expected Executive Value: Enables accurate project cost comparisons—critical for benchmarking and decision-making

## Phase 2: Mid-Term Structural Improvements (4-8 Weeks)

Priority Level: HIGH

2.1 Implement Predictive Analytics

Actions:

Build "Forecast Budget at Completion" model based on burn rate analysis

Add "Expected Completion Date" prediction using current progress velocity

Create risk probability scoring: likelihood of project failure based on historical patterns

Display predictions prominently with confidence intervals

Expected Executive Value: Transforms dashboard from backward-looking to forward-looking—enables proactive intervention before projects fail

2.2 Build Historical Vendor Analysis (20+ Years)

Actions:

Import historical contract and vendor data (20+ years if available)

Calculate long-term vendor performance metrics: average cost variance, on-time %, reliability

Create vendor track record dashboard showing historical performance

Add "Vendor Recommendation" feature: highlight vendors with best long-term performance for similar projects

Expected Executive Value: Supports strategic vendor selection for major multi-year contracts—reduces risk of poor vendor performance

2.3 Create Capital Project Pipeline View

Actions:

Build pipeline dashboard showing planned projects by fiscal year

Display: Project name, estimated cost, proposed start date, funding status

Add capacity analysis: "You have $15M budget capacity remaining for FY26"

Enable drag-and-drop prioritization of pipeline projects

Expected Executive Value: Enables multi-year capital planning and answers "Can we afford this project next year?"

2.4 Add Dollar Normalization (Inflation Adjustment)

Actions:

Integrate construction cost inflation index (e.g., ENR Construction Cost Index)

Add "inflation_adjusted_cost" calculated field to all historical contracts

Display historical cost comparisons in "constant dollars" (e.g., 2026 dollars)

Add toggle: "Show actual costs / Show inflation-adjusted costs"

Expected Executive Value: Enables accurate historical cost comparisons—answers "Are we paying more or less than we did 10 years ago?"

2.5 Implement District-Level Equity Analysis

Actions:

Calculate capital spend per student by school district (elementary, middle, high school zones)

Create geographic heat map showing investment distribution

Add equity dashboard: "District A has received 35% more per-student investment than District B over 5 years"

Provide equity score: How evenly are capital investments distributed?

Expected Executive Value: Addresses political/constituent concerns about fair resource distribution—critical for public trust

2.6 Build Project Risk Assessment Model

Actions:

Develop risk scoring model: Likelihood of failure × Financial impact

Risk factors: Vendor performance, project complexity, budget size, timeline, change order history

Display: "High Risk: 35% probability of >20% cost overrun"

Create "Project Risk Matrix" quadrant chart: Impact vs. Likelihood

Expected Executive Value: Provides data-driven risk assessment for go/no-go funding decisions

## Phase 3: Long-Term Advanced Analytics & Governance (9-16 Weeks)

Priority Level: MEDIUM (Future Enhancement)

3.1 Implement Scenario Planning & What-If Analysis

Actions:

Build scenario modeling tool: "What if we delay this project 6 months?"

Cost impact modeling: "What if material costs increase 15%?"

Portfolio optimization: "How should we prioritize projects to maximize ROI?"

Budget constraint modeling: "If budget is cut 10%, which projects should we defer?"

Expected Executive Value: Supports strategic planning discussions—executives can model different scenarios before making decisions

3.2 Add AI-Powered Insights & Recommendations

Actions:

Integrate Claude API (Anthropic) for automated insight generation

AI analyzes trends and generates natural language summaries

Example: "Vendor X's performance has declined 15% over last 3 quarters. Consider competitive rebid for next contract."

Provide AI-generated recommendations: "Based on historical data, approve Project Y but defer Project Z until Q3"

Expected Executive Value: Transforms dashboard into intelligent advisor—proactively surfaces insights executives might miss

3.3 Build Automated Board Report Generator

Actions:

Create "Generate Board Report" button that produces formatted PDF

Report includes: Executive summary, top projects, risks, recommendations, supporting charts

Customizable: Select which projects/topics to include in report

Branded template matching board presentation standards

Expected Executive Value: Eliminates manual report preparation—staff can generate board-ready reports in 5 minutes vs. hours

3.4 Implement Mobile-Optimized Executive View

Actions:

Create mobile app or mobile-optimized web view

Simplified layout for smartphone screens

Push notifications for critical alerts: "Project X exceeded budget by $500K"

Offline mode: Download executive summary for review without internet

Expected Executive Value: Executives can review portfolio status anytime, anywhere—increases engagement and responsiveness

3.5 Establish Governance & Continuous Improvement Framework

Actions:

Create dashboard governance committee (board members + staff)

Quarterly review: "Is the dashboard meeting board needs?"

Implement feedback mechanism: Executives can suggest improvements directly in dashboard

Track dashboard engagement analytics: Which sections are most viewed? Which are ignored?

Continuous refinement based on actual usage patterns

Expected Executive Value: Ensures dashboard remains relevant and valuable over time—avoids becoming stale or obsolete

# Conclusion

The Marion County Contract Oversight System possesses a strong technical foundation and comprehensive data infrastructure. The transformation to an executive-grade Board Decision Dashboard is not a rebuild—it is a focused refinement of the presentation layer and information architecture.

Key Success Factors:

Prioritize clarity over comprehensiveness—executives need insights, not data dumps

Implement quick wins first (Phase 1) to demonstrate immediate value

Replace sample data with real data before any board presentation—credibility is paramount

Separate land costs from construction costs—foundational for accurate analysis

Add forward-looking metrics—boards care more about what will happen than what happened

Establish governance framework to ensure continuous improvement

Recommended Next Steps:

Review this gap analysis with project stakeholders and board leadership

Prioritize Phase 1 quick wins for immediate implementation

Identify data sources for replacing sample data with real Marion County data

Schedule demo session with school board executives to gather direct feedback

Allocate resources for phased roadmap execution

Final Observation:

This dashboard has the potential to set a new standard for government transparency and data-driven decision-making in public education infrastructure. With focused refinement guided by this gap analysis, it can become the authoritative tool for all capital project decisions, demonstrating best practices in fiscal accountability and strategic planning.

— End of Gap Analysis Report —